## Slide 1: Progress Updates Operational Parameters & Progress Monitoring
For Pilot Q2/FY24Q3 progress For 4th CPC
Due: 2 Jan 2025

## Slide 2
Operational Parameter Updates
Milestones | Past 3 months | 
 | Next 3 months | 
Implementation challenges |  | 
Support requested (if any) |  | 
Institution: SACH
Updated as of 18 July 2024

## Slide 3: Dataset submission
Dataset | Implementation | Month (from initial patient recruitment) | Data Collection Period | Dataset submission* (Deadline)
Pilot Q1 data | 1st Quarter | Month 1 | FY24Q2 July to September 2024 | 30 November 2024 Submitted: 16 December 2024 (TBC)
 |  | Month 2 |  | 
 |  | Month 3 |  | 
Pilot Q2 data | 2nd Quarter | Month 4 | FY24Q3 October to December 2024 | 28 February 2025
 |  | Month 5 |  | 
 |  | Month 6 |  | 
Pilot Q3 data | 3rd Quarter | Month 7 | FY24Q4 January to March 2025 | 30 May 2025
 |  | Month 8 |  | 
 |  | Month 9 |  | 
Pilot Q4 data | 4th Quarter | Month 10 | FY25Q1 April to June 2025 | 29 August 2025
 |  | Month 11 |  | 
 |  | Month 12 |  | 
Subsequent submission of dataset to be determined |  |  |  | 
For SACH’s internal reference

## Slide 4: Progress Updates: Project and Dataset Info
Dataset Info | Site Update | Comments
Sample size data (Q1 + Q2) | 99 | No exit conditions triggered
Q1 dataset completion | (Complete / Ongoing / Not started) Submission by: December 2024 | 
Q2 dataset completion | (Complete / Ongoing / Not started) Submission by: ?? | 
Exit conditions met | No | 
Project Info | Site Update | Comments
Start of recruitment | 1st July 2024 | On track
Recruitment target | 45 patients/month (I2CH – 40 and C2CH – 5) | 
No. of patients: (to date) |  | 
Recruited | 128 (July & August 2024) | 
Discharged | 68 (July & August 2024) | 
Admitted to CH (overall) | 99 (July & August 2024) | 
Instructions for sites:
Please indicate the information requested accordingly:
Project information
Start recruitment date
Recruitment target (can specify per month or total size at the end of 18-month implementation)
Number of patients recruited and discharged to date
Please share comments and/or feedback where appropriate
Dataset info – relevant to the related data reported during the progress update
To share the sample size to be presented in the slide deck
To update on progress of dataset completion – mainly to find out if it will be on track for dataset submission for Q1 data
SACH
Highlighted: for SACH to amend
Up to 29/9/24
Notes: Recruitment – 114 + 14 = 128
I2CH – 58 + 56 = 114
C2CH – 8 + 6 = 14

## Slide 5: Progress Updates: Project and Dataset Info
Dataset Info | Site Update | Comments
Sample size data | 12 | (Please provide some detail and description on exit conditions met for any of the indicators of interest as part of monitoring) (Please share progress of Q1 data collection, if possible)
Q1 dataset completion* | (Complete / Ongoing / Not started) Submission by: (target date) | 
Exit conditions met | (Yes/No) | 
Project Info | Site Update | Comments
Start of recruitment | 17/07/2024 | Recruitment details in slide 5 Discharge details in slide 7
Recruitment target | 45 patients over course of 12 months | 
No. of patients: (accurate as of 27/09/24) |  | 
Recruited | 12 | 
Discharged | 8 | 
Admitted to CH (overall) | 12 | 
Instructions for sites:
Please indicate the information requested accordingly:
Project information
Start recruitment date
Recruitment target (can specify per month or total size at the end of 18-month implementation)
Number of patients recruited and discharged to date
Please share comments and/or feedback where appropriate
Dataset info – relevant to the related data reported during the progress update
To share the sample size to be presented in the slide deck
To update on progress of dataset completion – mainly to find out if it will be on track for dataset submission for Q1 data
*Note: Q1 dataset submission is due no longer than 2 months from preceding quarter
SACH
Highlighted: for SACH to amend
Up to 29/9/24

## Slide 6: Progress Updates: Project and Dataset Info
Dataset Info | Site Update | Comments
Sample size data | No. of patients included for the current progress update | (Please provide some detail and description on exit conditions met for any of the indicators of interest as part of monitoring) (Please share progress of Q1 data collection, if possible)
Q1 dataset completion* | (Complete / Ongoing / Not started) Submission by: (target date) | 
Exit conditions met | (Yes/No) | 
Project Info | Site Update | Comments
Start of recruitment | (dd/mm/yyyy) | (Comment on recruitment progress, e.g. Is recruitment on target or on track? To share challenges if any)
Recruitment target | (Expected pilot sample size or per month basis) | 
No. of patients: (to date) |  | 
Recruited |  | 
Discharged |  | 
Admitted to CH (overall) |  | 
Instructions for sites:
Please indicate the information requested accordingly:
Project information
Start recruitment date
Recruitment target (can specify per month or total size at the end of 18-month implementation)
Number of patients recruited and discharged to date
Please share comments and/or feedback where appropriate
Dataset info – relevant to the related data reported during the progress update
To share the sample size to be presented in the slide deck
To update on progress of dataset completion – mainly to find out if it will be on track for dataset submission for Q1 data
*Note: Q1 dataset submission is due no longer than 2 months from preceding quarter
For action (Each site to input)

## Slide 7: Progress Updates: Information on Control Group
Instructions for sites:
Please review and amend the information requested accordingly:
Pilot Group/Intervention Group and Control Group columns
Definition
Description – characteristics, including inclusion and exclusion criteria, sample size, recruitment method, period of recruitment/data collection
Please share comments and/or feedback where appropriate
*Note: Q2 dataset submission is due no longer than 2 months from preceding quarter (deadline end Feb ‘25)
SACH
For SACH to review information and amend or input accordingly
Information | Control/Comparator Group |  | Pilot/ Intervention Group
1. Approach & Definition of Group/Sample | Original input in technical manual: In our pilot study, historical controls will be selected from patient records from the past year (2023) between the months of January to September. These controls will be carefully matched to the pilot study participants based on the study inclusion criteria. By aligning historical controls with the participant profiles in the pilot study, we aim to characterize the heterogeneity of the disease effectively and evaluate how different factors influence treatment outcomes. This approach will provide a robust baseline for comparison and help to identify any potential biases or trends over time. |  | 
2. Recruitment Number/ Sample size | Sample Size, N = 21 |  | Recruitment target: 45
3. Description |  |  | 
a. Patient Profile | Inclusion/Exclusion Criteria: Same as pilot group’s (refer to slide 9) |  | Inclusion/Exclusion Criteria: Inclusion/exclusion criteria
b. Group characteristics | i. Casemix/DRG distribution n (%) | Fracture type n(%) LL hip: 2 (9.5%) LL non hip: 19 (90.5%) | (data collection still in progress)
 | ii. Patient Type (Subacute/Rehab) | Subacute: 21 (100 %), Rehab: (XX/Y) % | 
Demographics | iii. Age/Age group | Median Age: 75 years | 
 | iv. Gender | Male: 17 (81%), Female: 4 (19%) | 
 | v. Race | Chinese: 15 (71.4%) Malay: 3 (14.3%) Indian: 3 (14.3%) | 
4. Data | Available Data: Data from January to March 2023 will eventually be supplemented with data up to September 2023 to enable robust comparison with the intervention group Can data be shared with MOHT: Yes |  | 

## Slide 9: Inclusion/exclusion criteria
Inclusion Criteria Patients with pelvic / lower limb fractures status post operation or conservatively managed, requiring a time-limited period of non-weight bear (NWB) or toe touch weight bear (TTWB) Benefits from interim maintenance therapy or nursing / custodial care as a consequence of the weight-bearing limitation The eventual rehabilitation goal is to restore premorbid ambulatory /ADL function after this interim period Fulfil criteria of One Rehab Tier 2D or Tier 2 after the initial period of NWB/ TTWB Medically stable consecutively for 3 days Pain well controlled Age ≥ 65 years old Singapore Citizen and Subsidized patient (i.e. Class C and B2) | Exclusion criteria Pre-morbid status is chair or bed-bound with a Clinical Frailty Score of 6 and above Dementia with BPSD (moderate to severe) or Psychiatric disorders with significant behavioral issues (e.g. Schizophrenia / Major Depression, with significant apathy /poor participation) Patient with life life-limiting condition (i.e. with a prognosis ≤ 3 months) Patient can be discharged home with a referral to DRC (One rehab Tier 2) immediately post-acute care. Patient unable to return to pre-fracture residence Patient unable to return to premorbid ambulatory status - for chair-bound care e.g. periprosthetic # / conservative managed hip # Patient with a concurrent upper limb fracture with non or partial weight bear status (review later part) Hemodialysis patient

## Slide 10: Progress Update: Monitoring Overview
Comparator group/control group: in-development (baseline information was provided in pilot proposal)
Sample size (control group): in-development
SACH
Domain | Indicator | Comparator Group (Baseline)* (in-development) | Intervention Grp (17 Jul to 29 Sep 24) | Target met for Intervention Grp? | Remarks (For baseline group) | Remarks (For study group)
A. Patient Profile | Casemix/Patient Recruitment Subacute (On Admission) Rehab (On Admission) | 0 | 12 0 (0%) 12 (100%) | On track | Not specified | N=12 Target: 4/month (45 patients over course of 12 months)
B. Patient Safety | 2. U-turn rate within 72 hours | In-development | 1 (12.5%)2 | TBC |  | N=8 (discharged), (4 are in flight at time of reporting) Target: not higher than baseline or not higher than those who declined Mobile CH option (whiever is lower)
 | 3. 30-day related readmission | In-development | 0 (0%) | TBC |  | 
 | 4. Mortality | 0% | 0 (0%) 0 per 1,000 patient-days | = Yes |  | 
 | 5. (Adverse Events) Readmissions due to Clinical Deterioration /Complications | 11.1% | 6 (50%)1 | ↑No1 |  | N=12 See comments in Slide 27
C. Quality of Care | 6. Length of Stay (LOS)3 Average AH-CH LOS Average AH LOS Average CH LOS | 59.1 days 12 days 47.1 days | 33.5 days (AH-MoCH) 9 days 24.5 days (MoCH) | ↓Yes | N = 24 (Eligible LL NWB patients from Jan-Mar 2023) | N = 8 (discharged, all rehab) Target: AH-CH LOS, 44.3 days; AH LOS, 12 days; CH LOS 32.3 days
Note: *Baseline parameters reflected are provided by SACH through the MHI proposal is based on patients admitted from Jan to Mar 23 which fulfils the intended inclusion criteria for the pilot. 1. Readmissions to AH due to adverse events in the form of clinical deterioration/complications is counted towards Adverse Events, SREs were reportedly 0. Target is set as not higher than 11.1%. 2. Baseline not yet established, target will be based on baseline parameters. 3. LOS reflects physical inpatient stay, LOS (in brackets) incorporate MobileCH alternative site component.
For SACH’s Internal Reference
Notes: Patient profile: recruited 12 patients so far
Safety: 1 uturned within 72 hrs, adverse event rates were 50%, however we note that Readmissions to AH because of clinical deterioration/complications is counted towards Adverse Events, SREs were reportedly 0. will elaborate later
Comparator ALOS (still a work in progress to better define comparator group): however based on eligible LL NWB patients from Jan – March 2023
Average MoCH LOS is 24.5 days but that’s taking into account that were patients that were readmitted to AH for clinical deterioration. However pilot numbers are very small so it is hard to place much importance on LOS numbers for now.

## Slide 11: Progress Update: Monitoring Overview
Comparator group/control group: in-development (baseline information was provided in pilot proposal)
Sample size (control group): in-development
SACH
Domain | Indicator | Comparator Group (Baseline)* (in-development) | Intervention Grp (17 Jul to 29 Sep 24) | Target met for Intervention Grp? | Remarks (For baseline group) | Remarks (For study group)
A. Patient Profile | Casemix/Patient Recruitment Subacute (On Admission) Rehab (On Admission) | 0 |  |  |  | 
B. Patient Safety | 2. U-turn rate within 72 hours | In-development |  |  |  | 
 | 3. 30-day related readmission | In-development |  |  |  | 
 | 4. Mortality | 0% |  |  |  | 
 | 5. (Adverse Events) Readmissions due to Clinical Deterioration /Complications | 11.1% |  |  |  | 
C. Quality of Care | 6. Length of Stay (LOS)3 Average AH-CH LOS Average AH LOS Average CH LOS | 59.1 days 12 days 47.1 days |  |  |  | 
 | 7. Functional Outcomes MBI score (on admission) MBI score (upon-discharge) % improvement (or proportion of patients improved, remain stable, worsen) | XX XX XX | XX XX XX |  |  | 
Note: *Baseline parameters reflected are provided by SACH through the MHI proposal is based on patients admitted from Jan to Mar 23 which fulfils the intended inclusion criteria for the pilot. 1. Readmissions to AH due to adverse events in the form of clinical deterioration/complications is counted towards Adverse Events, SREs were reportedly 0. Target is set as not higher than 11.1%. 2. Baseline not yet established, target will be based on baseline parameters. 3. LOS reflects physical inpatient stay, LOS (in brackets) incorporate MobileCH alternative site component.
For SACH’s put
Notes: Patient profile: recruited 12 patients so far
Safety: 1 uturned within 72 hrs, adverse event rates were 50%, however we note that Readmissions to AH because of clinical deterioration/complications is counted towards Adverse Events, SREs were reportedly 0. will elaborate later
Comparator ALOS (still a work in progress to better define comparator group): however based on eligible LL NWB patients from Jan – March 2023
Average MoCH LOS is 24.5 days but that’s taking into account that were patients that were readmitted to AH for clinical deterioration. However pilot numbers are very small so it is hard to place much importance on LOS numbers for now.

## Slide 12: Progress Update: Site baseline, target and exit conditions
Domain | Indicator | Pilot Baseline | Target met? | Exit condition met?
 |  | SACH |  | 
A. Patient Profile | 1.Casemix/Patient Recruitment | 12 | (Yes/No/Not Applicable) | (Yes/No/Not Applicable)
B. Patient Safety | 2. U-turn | 1 (8.3%) | (Yes/No/Not Applicable) | (Yes/No/Not Applicable)
 | 3. 30-day related readmission | 0 (0%) | (Yes/No/Not Applicable) | (Yes/No/Not Applicable)
 | 4. Mortality | 0 (0%) | (Yes/No/Not Applicable) | (Yes/No/Not Applicable)
 | 5. Adverse Events | 6 (50%) | (Yes/No/Not Applicable) | (Yes/No/Not Applicable)
C. Quality of Care | 6. Length of Stay (LOS) | Mean: 24.5 days | (Yes/No/Not Applicable) | (Yes/No/Not Applicable)
Comparator group/control group: (Control group baseline had not been established)
For SACH’s input
SACH

## Slide 13: A. Patient Profile: Casemix Distribution i) Care Model x Subacute/Rehab
Domain | Indicator | Statistics
Patient Profile | 1. Casemix Distribution by Care Type | 
Mobile CH | No. of patients admitted into MobileCH (Total) | 12
 | Subacute | 0 (0%)
 | Rehab | 12 (100%)
Comments |  | 
(Please share total number of patients admitted into CH, including CHoF ward, during this period) All admitted to MobileCH [Please provide breakdown by diagnosis or RDG, if possible] ICD: S72.0 (x1) S72.1 (x3) S82.1 (x2) S82.3 (1) S82.6 (x2) S82.7 (x1) S82.8 (x2) RDG: Tier 2D [Please report breakdown of patients screened/referred/rejected if possible] Number of patients admitted to MoCH: 12 (Jul: 3, Aug: 7, Sep: 2) Number of patients approached: 15 Number of patients rejected: 3 Reasons for rejection: 1) Patient does not like TCF from sister's experience 2) Family does not like the environment in TCF 3) Patient prefer close monitoring in SACH than MoCH @Home, and daughter also feels not convenient for home visits due to privacy of other family members who are WFH. |  | 
SACH
Please specify patient recruitment period
At sites’ discretion to modify the template for ease of reporting
Comments box are for sites to share comments, remarks or notes relevant
Under “Statistics” please input fraction or percentage distribution where possible
Up to 29/9/24
For SACH’s input

## Slide 14: A. Patient Profile: Casemix Distribution ii) Care Model x Referral/Admission Source
Please specify patient recruitment period
At sites’ discretion modify the template for ease of reporting
Comments box are for sites to share comments, remarks or notes relevant
Please indicate N/A for cells which are not applicable
For “Others”, please specify
Under “Statistics” please input fraction or percentage distribution where possible
Domain | Indicator | Statistics
Patient Profile | 2. Casemix Distribution by Referral Source | 
MobileCH | No. of patients admitted into MobileCH (Total) | 12
 | Inpatient | 100%
 | Emergency | 0
 | Others | 0
Comments |  | 
Please specify “others” where possible |  | 
SACH
Up to 29/9/24
For SACH’s input
Notes: GTK - Nil

## Slide 15: A. Patient Profile: Casemix Distribution iii) Care Model x Discharge Disposition
Please specify patient recruitment period
At sites’ discretion modify the template for ease of reporting
Comments box are for sites to share comments, remarks or notes relevant
Please indicate N/A for cells which are not applicable
For “Others”, please specify
Under “Statistics” please input fraction or percentage distribution where possible
Domain | Indicator | Statistics
Patient Profile | 3. Casemix Distribution by Discharge Disposition | 
 | No. of patients admitted into MobileCH (Total) | 12
 | No. of patients discharged from MobileCH | 8
 | Home | 2/8 (25%)
 | Nursing Home | 0
 | Others ; Acute Hospital readmission* | 6/8 (75%)
Comments : |  | 
4 are still inflight. Nursing Homes were not included as a site of care in this pilot phase due to the wait time into NHs. *Refer to Slide 8 for reasons for readmissions |  | 
SACH
Up to 29/9/24
For SACH’s input
Notes: GTK : nil

## Slide 16: A. Patient Profile: Casemix Distribution iv) Care Model x Alternative Care site
Please specify patient recruitment period
At sites’ discretion modify the template for ease of reporting
Comments box are for sites to share comments, remarks or notes relevant
Please indicate N/A for cells which are not applicable
For “Others”, please specify
Under “Statistics” please input fraction or percentage distribution where possible
Domain | Indicator | Statistics
Patient Profile | 3. Casemix Distribution by Alternative Care site | 
 | No. of patients admitted into MobileCH (Total) | 12
 | No. of patients care for under MoCH alternative sites: | 12
 | Home | 1
 | Transitional Care Facility | 11 (91.7%)
 | Nursing Home | 0
Comments : |  | 
4 are still inflight. Nursing Homes were not included as a site of care in this pilot phase due to the wait time into NHs. *Refer to Slide 8 for reasons for readmissions |  | 
SACH
Up to 29/9/24
After note: under MoCH 1 patient cared for at home, 11 patients cared for in TCF
For SACH’s input
Notes: GTK : nil

## Slide 17: B. Patient Safety: By Care Model U-turn, 30-day related readmission, Mortality, Adverse Events
Please specify patient recruitment period
At sites’ discretion modify the template for ease of reporting
Comments box are for sites to share comments, remarks or notes relevant
Please indicate N/A for cells which are not applicable
For “Others”, please specify
Under “Statistics” please input fraction or percentage distribution where possible
Please review included definitions used to compute
Domain | Indicator | Statistics
Patient Safety | No. of patients admitted to MobileCH (Total)1 | 12
U-turn | No. of unplanned admissions after arrival to MobileCH 2 | 1/8 = 12.5%
30-day related readmission | Rate of admission to an acute hospital within 30 days of discharge from Mobile CH3 | 0 %
Mortality (Proportion) | Number of mortalities for patients admitted under Mobile CH4 | 0 % 0 per 1,000 patient-days
*Readmissions due to Clinical Deterioration/Complications | Number of readmissions to AH due to adverse event (deterioration/complications)5 (Refer to notes below) | 6/12= 50%
Comments |  | 
For the 12 patients admitted into the programme, 6 have dropped out of the programme through development of acute problems requiring readmission. 1 for intestinal obstruction due to adhesion (premorbid condition) – acute care 1 for acute exacerbation of COPD – this patient had subsequently passed away – acute care 1 for wound dehiscence requiring readmission for surgical intervention – acute care 1 for development of acute footdrop requiring further evaluation (MRI) –acute care 1 for SSI for ortho consultation, not requiring surgical intervention (readmission possibly prevented – by conversion to subacute care in CH) 1 for hyponatraemia due to poor intake and low mood – acute care Adverse Events (Refer to MOHT Technical Manual – SACH) based on (A) US Health and Human Services definition = 0 (B) SRE = 0 (C) MOH Safe care indicators (Falls, Med Errors, Pressure Injury, CAUTI) = 0 |  | 
Indicator Definition
U-turn (%): 2 Number of patients with unplanned admission to the Acute Hospital within 72 hours from admission to the Mobile CH due to an untoward change in patient’s condition/ 1 Total number patients admitted to MobileCH;
30-day related readmission (%): 4Number of urgent admissions into acute hospital within 30 days of discharge from Mobile CH/ Patients on NWB status s/p fracture with potential for rehabilitation and improvement of WB status discharged to Mobile CH
Mortality (%): 5 Number of mortalities in SACH CHoF Ward/ 1 Total number of patients enrolled into MobileCH
Adverse Events (%): 6 Number of readmissions to acute hospital due to clinical complication or deterioration/ 1 Total number of patients enrolled into MobileCH
SACH
Period: 17/7/24 to 29/9/24
For SACH’s input
Notes: GTK : nil

## Slide 18: C. Quality of Care: Length of Stay (no. of days)
Domain | Indicator | Statistics | 
Quality of Care (Length of Stay) |  | Rehab | 
 | Number of discharges of CHoF patients | 8 | 
Overall AH-CH average length of stay | A1. Total AH-MobileCH LOS1 (no. of days) A2. Total AH-CH LOS (no. of days) | 72 +196 = 268 (n=8) 72+0=72 (n=8) | Range: (Min, Max)
 | B1. Average or median AH-MobileCH LOS (no. of days) B2. Average or median AH-CH LOS (no. of days) | 268/8 =33.5 72/8=9 | 
AH average length of stay | Total AH LOS2 (no. of days) | 72 (n=8) | Range: (Min, Max)
 | Average or median AH LOS (no. of days) | 72/8= 9 | 
CH average length of stay | A1. Total MobileCH LOS3 (no. of days) A2. Total CH LOS (no. of days) | 196 (n=8) 0 (n=8) | Range: (Min, Max)
 | A3. Total MobileCH LOS (Excluding exits/re-admissions) A4. Total CH LOS (Excluding exits/re-admissions) | 101 (n=2) 0 (n=2) | Range: (Min, Max)
 | B1. Average or median MobileCH LOS (no. of days) B2. Average or median CH LOS (no. of days) | 196/8= 24.5 0/8=0 | 
 | B3. Average of median MobileCH LOS (Excluding exits/re-admissions) B4. Average or median CH LOS (Excluding exits/re-adm) | 101/2= 50.5 0/2=0 | 
Comments: (If possible, please report min, and max LOS) (Please report if there are outliers, exit conditions met, or targets are met/not met) |  |  | 
SACH
1 Sum of length of stay in acute hospital and MobileCH (alternative CH site); 2 Length of stay from admission into acute hospital to discharge from acute hospital to MobileCH (AH component); 3 Length of stay from admission into MobileCH to discharge
Period: 17/7/24 to 29/9/24
For SACH’s input

## Slide 19: C. Quality of Care: Functional Outcomes Care Model X Care Type
Domain | Indicator | Statistics | 
Quality of Care (Functional Outcomes) |  | Rehab | 
 | Number of patients discharged from care model |  | 
MBI score (on admission) | Average MBI (on admission) | xx | Range: (min, max)
 | Median MBI (on admission) | xx | 
MBI score (upon discharge) | Average MBI (upon discharge) | xx | Range: (min, max)
 | Median MBI (upon discharge) | xx | 
Percentage Improvement | Average Percentage Improvement | XX % | Range: (min, max)
 | Median Percentage Improvement | XX % | 
Improvement by Proportion of patients | Proportion of patients who improved | XX % | 
 | Proportion of patients who remain stable | XX % | 
 | Proportion of patients who worsen | XX % | 
SACH
Patient Recruitment Period: (July and August 2024)
For JCH’s Input
Notes: C2CH – 1 discharged to AH and 1 TDRA
I2CH – 6 discharged to AH and 2 TDRA

## Slide 20: [Optional] D. Programme Optimisation and Efficiency Cost (to patient) Outcomes
Domain | Indicator | Statistics
Programme Optimisation and Efficiency |  | I2CH ($)
Hospitalization Bill (Gross) | Average or median patient Hospitalization bill (combined AH & CH) | XX
 | Average or median patient Hospitalization bill (AH only) | XX
 | Average or median patient Hospitalization bill (CH only) | XX
Out of Pocket (OOP) Utilization | Average or median OOP component (combined AH & CH) | XX
 | Average or median OOP component (AH only) | XX
 | Average or median OOP component (CH only) | 
Comments |  | 
Patient Recruitment Period: (please specify)
SACH
Do not remove [Hide slide if n/a]

## Slide 21: Progress Update: Site baseline, target and exit conditions
Domain | Indicator | Baseline | Target | Exit condition
A. Patient Profile | 1.Casemix/Patient Recruitment | 0 | 4/month | Less than 10 patients in 6 months
B. Patient Safety | 2. U-turn | TBC | Rate not higher than baseline and not higher than those who declined Mobile CH option even though eligible (whichever is the lower). | None
 | 3. 30-day related readmission | TBC | 30-day readmission rate to acute hospital equivalent or not worse than retrospective cohort | None
 | 4. Mortality | 0% | 0% | 2 SRE with detected safety lapses and/or if patient selection criteria requires review
 | 5. Adverse Events | 11.1 % | Not higher than 11.1 % | AER higher than baseline or eligible cohort not admitted to Mobile CH for 3 consecutive months
C. Quality of Care | Length of Stay |  |  | 
 | Combined AH-CH ALOS | 59.1 days | 44.3 days | Increase in AH-CH LOS after 6 months
 | AH ALOS | 12 days | 12 days | None
 | CH ALOS | 47.1 days | 32.2 days | Increase in CH LOS after 6 months of programme
Comparator group/control group: (Please describe comparator group for the evaluation of pilot)
Internal reference for SACH
(not to be shared with all sites)
SACH
(Hidden slide) Do not remove